## Slide 1: Why Replace-in-Kind when You Can Build it Better? Performance Improvements from Rehabilitation of an Aging Nitrifying Facility
May 16, 2025
Samir Mathur, P.E., BCEE
TACWA Meeting

## Slide 2: Agenda
San Gabriel Wastewater Treatment Plant (WWTP) Overview
Design Considerations
Maintenance of Plant Operations
Lessons Learned
Wet Weather Basin
Aerated Sludge Holding Tank
Clarifiers
Treatment Units
Headworks
Grit Facility
Blowers
Sludge Drying Beds (rarely used)

## Slide 3: San Gabriel Wastewater Treatment Facility

## Slide 4: Plant Background
1981: Contact Stabilization Plant
1990’s: Ammonia Limit Added to Permit
2011 and 2019: Misc. Plant Improvements
2023-2025: Design and Construction of Rehabilitation Project
2021: Facility Planning Technical Memorandum

## Slide 5: Georgetown, Texas
Growing suburb outside of Austin
Located along I-35 corridor
High growth in tech companies

## Slide 6: Population Growth
Chart: Population in Georgetown
| 2022 | 2021 | 2020 | 2019 | 2018 | 2017 | 2016 | 2015 | 2014 | 2013 | 2012 | 2011 | 2010 | 2009 | 2008 | 2007 | 2006 | 2005 | 2004 | 2003 | 2002 | 2001 | 2000 | 1999 | 1998 | 1997 | 1996 | 1995 | 1994 | 1993 | 1992 | 1991 | 1990
 | 86507 | 75420 | 68227 | 79745 | 74350 | 70667 | 67058 | 63566 | 59003 | 54854 | 52499 | 50322 | 48019 | 52131 | 49618 | 46784 | 42784 | 39581 | 36937 | 35453 | 33872 | 32371 | 29476 | 32368 | 29705 | 26609 | 23278 | 21254 | 19833 | 17613 | 16862 | 16233 | 16117

## Slide 7: WWTPs Nearing Capacity

## Slide 8: San Gabriel Wastewater Treatment Plant
City of Georgetown’s (CoG) oldest wastewater treatment plant operating at 90-100% of design capacity
Cannot expand due to ban on new discharges to Edwards Aquifer recharge zone
  CDM Smith designed ability for San Gabriel WWTP to divert flow to Dove Springs WWTP and to store and transfer flow to Pecan Branch WWTP to allow for maintenance activities
City is a rapidly growing community for over a decade

## Slide 9: Treatment Structure Process Flow – Contact Stabilization
REAERATION ZONE #2
REAERATION ZONE #1
CONTACT MIX 2A
CONTACT MIX 1A
CONTACT MIX 2B
CONTACT MIX 1B
CHLORINE CONTACT
CHLORINE CONTACT
CLARIFIER #2
CLARIFIER #1
24” DEGRITTED INFLUENT
DISTRIBUTION BOX

## Slide 10: Treatment Structure Process Flow – 1990s
REAERATION ZONE #2
REAERATION ZONE #1
CONTACT MIX 2A
CONTACT MIX 1A
CONTACT MIX 2B
CONTACT MIX 1B
CHLORINE CONTACT
CHLORINE CONTACT
CLARIFIER #2
CLARIFIER #1
24” DEGRITTED INFLUENT
DISTRIBUTION BOX

## Slide 11: Existing Treatment Processes
Screenings + Headworks
Grit Removal
Secondary Treatment
Clarification
Chlorine Contact

## Slide 12: Grit Removal Basin
(2) Aerated grit chambers with draft-tube style aerator and airlift for grit slurry removal
Original design sent degritted raw wastewater through a single 24” pipe to distribution box between reaeration and contact mix zones
Issues Noted:
  Walls have overtopped – 24” pipe clogged
  Clogging of airlift pipe
  Grit classifier required replacement after 40 years

## Slide 13: Secondary Treatment
Converted in 1990’s with the addition of an ammonia limit
Contact stabilization is not allowed as a process for nitrifying facilities
Low-cost conversion to a step feed process was implemented using airlift pumps from the grit effluent channel
    Balanced food / microorganism ratio
    Good sludge settleability in clarifiers
Uses single drop coarse bubble diffusers

## Slide 14: Design to Construction

## Slide 15: Need for Rehabilitation
Replace aging equipment
Modernize treatment technologies
Improve treatment performance

## Slide 16: Hydraulic Analysis
Full hydraulic profile analysis to review proposed improvements:
    New grit removal technology
    New aeration basin influent (ABI) pipeline to retain step feed approach
Understand grit basin overtopping
New 20” ABI to Front of Aeration Basin
Existing 24” Degritted raw to Distribution Box
Existing 18” RAW to Grit Facility

## Slide 17: Step Feed Process and Hydraulic Analysis
New 20” influent to front of aeration basins allows for more permanent and reliable solution for partial plug flow.
Design to keep step feed approach:
  Passive hydraulic flow split had limitations at peak 2-hour flow
    75% of Flow - Route new 20” influent from grit
    25% of Flow - Utilize existing 24” DI to distribution box

## Slide 18: Grit Facility Rehabilitation Design
Conversion of one of two tanks to a stacked tray grit removal system
    Significantly greater removal efficiency of fine grit particles
Retrofit and modifications of existing tankage was feasible with Manufacturer
Use of slide gates to allow for operational flexibility with bypassing

## Slide 19: Secondary Treatment Improvements
Replacement of coarse bubble diffusers with fine bubble diffusers
New multistage blowers and low-pressure air lines

## Slide 20: Secondary Treatment Improvements
Critical sequence of construction to keep half the plant running during installation of new equipment

## Slide 21: Maintenance of Plant Operations (MOPO)

## Slide 22: Bypass Creativity to Keep the Plant Running
Contract required bypass pumping, however contractor thought of more creative, cost-effective approach to eliminate need of pumping
Temporary pipe connection from headworks to permanent 20” ABI piping to bypass grit facility using gravity
Temporary airlifts on the 20” ABI piping to continue step feed flow path
Use of hydraulic modeling to confirm new flow path didn’t disrupt existing hydraulic profile
Temporarily Divert Flow over Basin Wall
Temporary Tie Into Permanent Line
Permanent 20” Pipe
Existing 18” RAW from Headworks

## Slide 23: Bypass Creativity to Keep the Plant Running
Connecting to Existing 18” RAW to Bypass Grit Facility
Temporary Airlifts
Temporary Routing of Piping Up and Over Wall
Existing 18” RAW to Grit Facility
New 20” ABI to Front of AB
Airlift and Piping

## Slide 24: Slide Gate Replacement
Concrete coring of wall between aeration basin zones to aid in distribution box gate replacement
  Eliminated need for bypass pumping
Hole must be patched and repaired upon completion of work

## Slide 25: Lessons Learned

## Slide 26: Lessons Learned and Embracing the Unknown of Rehabilitation Projects
Construction phase of projects requires accountability and adaptability
Establishing rapport with the operations staff who live and breathe the facility
Understanding construction sequencing and practicality is a critical aspect to consider during the design phase
Importance of record drawings!

## Slide 27: Acknowledgements
CDM Smith: Alex Doody, Chris Varnon, and Allen Woelke
City of Georgetown Staff: Chelsea Solomon, Chris Pousson, Tim Walker, Larry Taylor, Joshua Naylor, Tony Medlock, and Randall Swenson
Matous Construction: Blake Pitts and John Yanez

## Slide 28: Thank You
To learn more, please reach out to:
Samir Mathur, PE, BCEE Global Water Reclamation Practice Leader CDM Smith MathurS@CDMSmith.com 214-346-2800
Connect with me on LinkedIn: